## Sheet1
AFRICA CENTRES OF EXCELLENCE (ACE)
CERHI UNIVERSITY OF BENIN
| CMP XX | [7 empty] | Year 2016
Activity No | COMPONENT | SUB-COMPONENT | ACTIVITIES | OBJECTIVE | JUSTIFICATION | OUTPUT | ESTIMATED BUDGET ($) | RESPONSIBLE UNIT | January - December 2016
[9 empty] | January | Febrary | March |  | April | May | June | July | August | September |  | October | November | December
Component 1: Strengthening Africa Centers of Excellence
1 | Clearance and orientation for for New Postgraduate students |  | Procure Orientation Handbook,Stationeries and Lecture Materials. | To expose new students to their new learning environment. | To ensure proper adjustment to expectations of the Centre to actualise the Bank's policies | 20 lectures. | 7500 | PMC
2 | Completion of CERHI building |  | 100% Completion of CERHI Complex with Seminar rooms, library labs completed with ESMP conformity certificate | To provide adequate accommodation for CERHI academic and research activities. | To provide a conducive teaching-learning environment for CERHI faculty and students and ensure sercurity and safety of all CERHI equipment |  | 282000 | Centre Leader/Co centre leader, DPP
3 | Procurement and installation of furniture for offices, seminar rooms and library |  | procuring and equipping the CERHI Center complex with furnishing for offices , seminar rooms and library with Center in use by students. | To provide effective teaching and learning environment. | To enhance effective capacity building. |  | 100050 | Centre leader, Co Centre leader, Procurement officer, financial officer, internal auditor
4 | Procurement and installation of e-learning platform, libraries, video conferencing |  | Equipping the CERHI Center complex with e-learning platform., libraries, video conferencing and in use by students. | To provide learning supplies for student for effective teaching and learning | To enhance effective capacity building. |  | 147000 | Centre leader, Co Centre leader, Procurement officer, financial officer, internal auditor
5 | Procurement and installation of equipment in CERHI laboratory |  | Purchase and installation of lab equipment for CERHI, including HIV and Reproductive Health research | To provide adequate research and training environment. | To provide adequate innovative research skills development. |  | 169159 | Centre leader, Co Centre leader, Procurement officer, financial officer, internal auditor
6 | Renovation of hostel and visiting faculty guest house |  | 100% completion of renovated foreign students accommodation and visiting faculty guest house | To provide hostel accomodation for students and comfort for visiting faculty. | Enhancement of comfortable and healthy resting place for students and faculty and effective preparation for continous readiness for academic activity. |  | 140692 | Centre leader, Co Centre leader, Procurement officer, financial officer, internal auditor, DPP
|  |  | Total |  |  |  | 846401
AFRICA CENTRES OF EXCELLENCE (ACE)
CERHI UNIVERSITY OF BENIN
| CMP XX | [7 empty] | Year 2016
Activity No | COMPONENT | SUB-COMPONENT | ACTIVITIES | OBJECTIVE | JUSTIFICATION | OUTPUT | ESTIMATED BUDGET ($) | RESPONSIBLE UNIT | January - December 2016
[9 empty] | January | Febrary | March |  | April | May | June |  |  |  | August | October | November | December
July
Component 1: Strengthening Africa Centers of Excellence
7 | 1st Quarter Expanded Project Management Committee (EPMC) Meeting . | [5 empty] | 15000 | PMC
8 | Research workshop |  | Research presentation from 8 research teams | To present and assess results from on-going researches from researchers in the thematic CERHI areas. | To ensure optimum research output and publications in high impact journals |  | 10000 | PMC
9 | Students Internship/Faculty Exchange |  | Exchange of students and faculty between partner institutions. | To expose and improve on the research capacity of students and faculty. | To update and enhance innovative research capacity in student and faculty. |  | 120000 | Centre leader, Co centre leader, Academic board
10 | Lectures and end of semester examination |  | Teaching and evaluation of students. | To provide an effective evaluation of students learning. | To provide a comprehensive assessment of the magnitude of teaching-learning situation in the four departments. |  | 120000 | HODs, Secretariat
11 | Purchase of a Sport Utility Vehicle (SUV) with registration. |  |  | Provision of official movement and effective utility services. | To provide prompt and effective service delivery. |  | 32361 | Centre leader
|  |  | Total |  |  |  | 297361
AFRICA CENTRES OF EXCELLENCE (ACE)
CERHI UNIVERSITY OF BENIN
| CMP XX | [7 empty] | Year 2016
Activity No | COMPONENT | SUB-COMPONENT | ACTIVITIES | OBJECTIVE | JUSTIFICATION | OUTPUT | ESTIMATED BUDGET ($) | RESPONSIBLE UNIT | January - December 2016
[9 empty] | January | Febrary | March |  | April | May | June |  |  |  | August | October | November | December
July
Component 1: Strengthening Africa Centers of Excellence
12 | Ist short course. |  |  | Capacity building for health personnels and administrators | Training of Health personnels from MDAs in Reproductive Health |  | 7500 | Project co-ordinator, PMC members and Secetariat
13 | Training of students/faculty on website (NGREN) utilisation |  |  | Training on Website utilisation. | Necessary retooling for greater accomplishments. |  | 8000 | PMC members and Secretariat
14 | Workshop on research methodology (Phase II) |  |  | Capacity Building for Centre's Academic Staff. | Achieve upgrade of New opportunities in research breakthough. |  | 7500 | PMC Members and Secretariat |  |  |  | 2016-04-08
15 | Training on uses of computersoftwares for analyses (Phase II). |  |  | To improve the usage of new software by Academics Audit, Accounts and Administrative Staff. | To update Staff on the use of applicable Software for Centre's activities. |  | 7500 | Project Coordinator, PMC Members and Secretariat
|  |  | Total |  |  |  | 30500
AFRICA CENTRES OF EXCELLENCE (ACE)
CERHI UNIVERSITY OF BENIN
| CMP XX | [7 empty] | Year 2016
Activity No | COMPONENT | SUB-COMPONENT | ACTIVITIES | OBJECTIVE | JUSTIFICATION | OUTPUT | ESTIMATED BUDGET ($) | RESPONSIBLE UNIT | January - December 2016
[9 empty] | January | Febrary | March |  | April | May | June |  |  |  | August | October | November | December
July
Component 1: Strengthening Africa Centers of Excellence
16 | Retreat for PMC Members. |  |  | To review Center's goals accomplishments and take decisions on next steps. | Necessary retooling for greater accomplishments. |  | 8000
17 | 2nd Quarter EPMC Meeting | [5 empty] | 15000 | Deputy Centre Leader and Secretariat
18 | 2nd Short Course: Economic evaluation of health intervention programmes |  | Training faculty/students on cost optimisation in healtjh facilities. | To enhance Capacity Building for Health Personnel in Reproductive Health among MDAs | Skill acquisition in effective resources Mgt. and value for money among MDAs |  | 7500 | PMC Members and Secretariat | [6 empty] | 2016-06-11
19 | Curriculum Review Workshop |  |  | Review of Centres Curriculum in all areas of specialisation | To ensure and update CERHI curricula in line with current and standard practice world over. |  | 7500 | PMC Members and Secretariat
20 | 3rd Short Course |  |  | Capacity Building for Health Personnel and Health Administrators | To enhace ade quacy of human capital in health and innovation in health productivity |  | 7500 | PMC Members and Secretariat |  |  |  | 2016-04-08 |  |  |  | 2016-05-08
21 | 3rd EPMC Meeting | [5 empty] | 10000 | Centre Leader, PMC members and Secretariat
|  |  | Total |  |  |  | 55500
AFRICA CENTRES OF EXCELLENCE (ACE)
CERHI UNIVERSITY OF BENIN
| CMP XX | [7 empty] | Year 2016
Activity No | COMPONENT | SUB-COMPONENT | ACTIVITIES | OBJECTIVE | JUSTIFICATION | OUTPUT | ESTIMATED BUDGET ($) | RESPONSIBLE UNIT | January - December 2016
[9 empty] | January | Febrary | March |  | April | May | June |  |  |  | August | October | November | December
July
Component 1: Strengthening Africa Centers of Excellence
23 | 4th short course |  |  | Capacity building for health personnels and administrators | Training of Health personnels from MDAs in Reproductive Health |  | 7500 | PMC Members and Secretariat
24 | Capacity Building |  |  | Improving faculty teaching methods and faculty development | Training of faculty / PMC members outside the country |  | 100000 | Centre Leader, Co Centre Leader and Secretariat
25 | 4th EPMC Meeting | [5 empty] | 15000 | Co Centre Leader and Secretariat
26 | International Advisory Board Meeting (IAB) | [5 empty] | 30000 | PMC Members and Secretariat
|  |  | Total |  |  |  | 152500
|  |  |  | Grand Total |  |  | 1382262